S100WG – Compendium of open Actions

| Actions |  |  |  | Status update - 20230531 |
| --- | --- | --- | --- | --- |
| Ref. | What | Who | By When |  |
| S100WG2-01 | Provide content to LinkedIn and coordinate creation of a WG page within ICSM web presence. | ZJ | AUG2023 | Little progress but ON TRACK |
| S100WG2-02 | The AHO to appoint a lead person to commence and coordinate the work of an ‘Australia S100 Testbed project’. | AS | JUN2023 | In Progress – New ‘S100 Coordinator’ role (appointment expected by mid June) |
| S100WG2-03 | S100WG members to seek support from their organisations and appoint a staff member to work with the S100 Testbed focus team. | All | JUN2023 | Please submit names to me by 15/06/2023. |
| S100WG2-04 | AMSA to invite GA to participate in their upcoming ‘Promulgation of Marine Park Information’ meeting (29/3/23) | SH | ASAP | DONE |
| S100WG2-05 | Update ToR based on the outcome of the discussions held at the meeting and circulate draft for final approval. | AS | MAY2023 | DONE (alongside the minutes of 2nd meeting) – No comments received so far. |
| S100WG2-06 | ToR – Annex A - Review mapping of S-nnn products against stakeholders. Support mapping or recommend action. | All | JUN2023 | No comments received so far. |
| S100WG2-07 | ToR – Prepare drafts for S100WG Roadmap and Work Plan. | AS | JUN2023 | Not started - I will make sure a draft is prepared before our 3rd meeting in August. |
| S100WG2-08 | Coordinate with AMSA so an S100WG hybrid meeting can be organised back to back with NSAG’s meeting in August 2023. | AS | MAY2023 | DONE and agreed in principle – Will keep in touch with AMSA to coordinate the execution. |
| S100WG2-09 | Set up S100WG collaborative space using MSTeams | ZJ | JUN2023 | Not started - I will coordinate with Zarina and try to have it up and running by the end of June. |